The Green Hub — Sustainable Community Center

MBA Team Final Project – Group 5 – July 6, 2025

RBC MBA — Project Management · Instructor: Dr. Ehab EL Nezamy

About

The Green Hub is a community center powered entirely by renewable energy, combining construction, engineering, and sustainability. It exemplifies integrating project management with sustainable development, providing environmental, social, and economic benefits to the community.

- Renewable energy

- Smart technologies

- Environmentally Responsible Design

The project aims to inspire greener communities and create a lasting positive impact, while fostering a culture of green living.

The Green Hub serves as a sustainable community center fueled by renewable energy and advanced smart technologies. It combines environmental education, community services, and eco-friendly design to generate lasting social, environmental, and economic benefits.

Team

Deliverable 1 — Scope Statement

| Component | Content |
| --- | --- |
| Description | Sustainable community center promoting environmental awareness and green living: renewable-energy-powered facility with smart technologies, educational workshops, recycling programs, coworking spaces, community activities. |
| Requirements | Solar PV system · smart lighting & HVAC controls · rainwater harvesting · recycling center · Building Management System (BMS). |
| Deliverables | Approved charter · architectural & engineering designs · completed sustainable building · renewable energy system · Smart BMS · community training program · final handover documentation. |
| Boundaries | IN: site prep, building construction, solar PV, rainwater, smart lighting/HVAC, native-plant landscaping, recycling center, training rooms, grand opening. OUT: other cities, residential, commercial retail, post-handover operation. |
| Assumptions | Funding approved · permits on time · materials available · skilled contractors available · stable weather. |
| Constraints | $1.2M budget · 40 weeks · LEED standards · local regulations · site limitations. |
| Strategy | Waterfall-dominant life cycle: sequential initiation, planning, design, procurement, construction, testing, and handover. The Smart Building Management System (BMS) is delivered incrementally through configuration, integration, testing, and commissioning. Agile is not used because the overall scope, budget, and 40-week timeline are fixed. |
| Acceptance criteria | ≤ 40 weeks · budget variance < 5% · LEED certified · smart systems operational · client satisfaction ≥ 90% · zero lost-time accidents. |
| Cost breakdown | Direct activity costs: Design $60K · Construction $570K · Solar PV $120K · Smart Systems/BMS $80K · MEP $140K · Landscaping $40K · Furniture $70K = $1,080K. Contingency reserve: $78K. Management reserve: $42K. Total approved budget: $1,200K. |

Life Cycle Selection & Justification

Waterfall is the governing life cycle for the sequential physical works because the requirements, approvals, construction sequence, acceptance criteria, budget, and completion date are defined in advance.

Incremental delivery is limited to the BMS: core monitoring is configured first, followed by HVAC and lighting integration, renewable-energy data, dashboards, and final commissioning. Each increment adds usable functionality against a predefined scope.

Agile is not selected because the project does not allow an evolving overall scope or an open-ended timeline. Controlled changes are processed through formal change control.

Deliverable 2 — WBS

Deliverable 3 — OBS

| Title / Organizational Role | Seniority Level | Assigned Member / Source | Report to |
| --- | --- | --- | --- |
| Sponsor / Account director | Executive Level | Internal company appointment | Executive Board |
| Project Manager | Top Management | Armia | Sponsor |
| Planning & Scheduling Lead | Lead Level | Ehab | Project Manager |
| Scope & Risk Officer | Lead Level | Amira | Project Manager |
| Finance & Partners Officer | Lead Level | Salwa | Project Manager |
| QA & Governance Officer | Lead Level | Shehab | Project Manager |
| QA & Audit Assistant | Junior Level | Michael | QA & Governance officer |
| Procurement & Supply Chain Lead | Lead Level | Internal company appointment | Project Manager |
| Sustainability & BMS Engineer | Senior Level | Internal company appointment | Project Manager |
| HSE Lead officer | Senior Level | Internal company appointment | Project Manager |
| Design, site, MEP and civil engineers | Senior Level | External consultants / contractor | Project Manager |
| Junior site & Field Engineers | Junior Level | Contractor | Project Manager |
| Site Supervisors & Foramen | Supervisory Level | External main contractor | Project Manager |
| Skilled trades & Equipment operators | Skilled Workforce | External main contractor | Site supervisor |
| General Construction Workers | General Workforce | External main contractor | Foramen |

Equipment & Resource Breakdown

| Category | Resource / Equipment | Inside Company | Outside Company | Total / Basis |
| --- | --- | --- | --- | --- |
| Management | Sponsor, PM, controls, finance, procurement, QA/QHSE, sustainability/BMS, community liaison | 9 | 0 | 9 people |
| Design & engineering | Architects, civil/structural, MEP, solar and landscape engineers | 0 | 8 | 8 people |
| Construction supervision | Construction manager, senior engineers, site engineers and supervisors | 0 | 10 | 10 people |
| Workforce | Skilled trades, equipment operators and general workers | 0 | 32 | 32 peak workers |
| Specialists | BMS integration, testing/commissioning and LEED support | 1 | 5 | 6 people |
| Office resources | Laptops, PM software, document control and meeting facilities | 10 sets | 0 | Company-owned |
| Heavy equipment | Excavator, loader, mobile crane, compactor, concrete pump/mixer and dump trucks | 0 | 8 units | Rented/contractor-owned |
| Technical equipment | Surveying sets, PV installation tools and MEP/BMS test kits | 2 sets | 9 sets | 11 sets |
| Safety & temporary works | PPE sets, scaffolding, edge protection and site barriers | 0 | 40 PPE + site sets | Contractor-provided |

Resource basis: internal staff govern and control the project; external consultants and contractors execute design, construction, specialist installation, and peak site labor. Counts are peak planning estimates and remain within the approved direct-cost baseline.

Deliverable 4 — Project Budget

PMBOK cost-aggregation case study: activity costs are aggregated first; contingency reserves are then added to establish the cost baseline, followed by management reserve to establish the approved project budget.

Operational Cost Levels

- Activity Cost Level: $1,080K in estimated direct costs for labor, equipment, materials, and professional services.

- Work Package Level: $38K activity contingency is added above activity costs, producing $1,118K in work-package cost.

- Control Account Level: a further $40K work-package contingency is added above work-package cost, producing the $1,158K cost baseline.

Green Hub Budget Matrix

| Cost Aggregation Level | Amount | Reserve Ratio | Cumulative |
| --- | --- | --- | --- |
| Direct Activity Costs | $1,080K | – | $1,080K |
| Activity Contingency Reserve | +$38K | 3.52% of activity cost | $1,118K |
| Work Package Cost | $1,118K | – | $1,118K |
| Work Package Contingency Reserve | +$40K | 3.58% of work-package cost | $1,158K |
| Cost Baseline / Control Accounts | $1,158K | – | $1,158K |
| Management Reserve | +$42K | 3.63% of cost baseline | $1,200K |
| Total Approved Project Budget | $1,200K | 10.00% of approved budget is reserves | $1,200K |

Financial Overview

Total Approved Budget: $1,200,000

- $1,080,000 (90.0%): direct activity execution, resources, and technical deliverables.

- $78,000 (6.5%): total contingency reserves for known risks across activities and work packages.

- $42,000 (3.5%): management reserve for unforeseen risk events.

Deliverable 5 — Stakeholder Analysis

Stakeholders were assessed using four clear categories only: H H, H L, L H, and L L. Customer/Investor, Sponsor, and Project Manager are treated as separate stakeholders. Municipality/Local Authorities are H L—not H H—because they have high regulatory power but comparatively low day-to-day interest beyond compliance and permits.

Quadrant Summary

- H H — Manage Closely: Customer/Investor · Sponsor · Project Manager · Main Contractor · Design Consultant

- H L — Keep Satisfied: Municipality/Local Authorities · Environmental Authority

- L H — Keep Informed: Site Engineers & Supervisors · Skilled and General Workers · Local Community · Key Suppliers

- L L — Monitor: General Public · Non-critical Vendors

Project Schedule Overview – Details in the Excel Sheet

The table and Gantt chart use the same start/end weeks. FS governs the major phase gates; SS with a stated lag is used only for approved overlaps. No SF relationship is required in this high-level schedule.

| Phase / WBS Branch | Start | End | Duration | Predecessor / Relationship | WBS Ref |
| --- | --- | --- | --- | --- | --- |
| Project Management (continuous) | 1 | 40 | 40 weeks | Project start (SS) | Branch 1 |
| Initiation | 1 | 2 | 2 weeks | Project start | 1.1 |
| Planning | 3 | 5 | 3 weeks | Initiation (FS) | 1.2–1.4 |
| Design & Engineering | 6 | 11 | 6 weeks | Planning (FS) | Branch 7 |
| Procurement | 12 | 15 | 4 weeks | Design & Engineering (FS) | Branch 8 |
| Site Preparation | 16 | 19 | 4 weeks | Procurement (FS) | Branch 2 |
| Building Construction | 18 | 28 | 11 weeks | Site Preparation (SS + 2 weeks) | Branch 3 |
| Green Systems Installation | 24 | 32 | 9 weeks | Building Construction (SS + 6 weeks) | Branch 4 |
| Landscaping & Outdoor Areas | 29 | 35 | 7 weeks | Building Construction (FS) | Branch 5 |
| Community Programs & Launch | 33 | 40 | 8 weeks | Green Systems (SS + 9 weeks) | Branch 9 |
| Testing | 36 | 38 | 3 weeks | Landscaping (FS); Green Systems complete | 6.1–6.2 |
| Handover | 39 | 40 | 2 weeks | Testing (FS) | 6.3–6.4 |

The Green Hub 40 Week Gantt Chart

Risk Mitigation Sheet for The Green Hub

| # | Risk | Probability |  | Impact Cost (USD) | Impact Time | Owner |  | Mitigation / Cost Effect |  | Solution Cost (USD) | Type |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Building permit delay | High |  | $17,600 (1.47%) | 4 wks | Design Lead |  | Submit at 70% design; appoint permitting consultant. Cost is added to prevention/consultancy. |  | $6,000 | MITIGATE |  |
| 2 | Late delivery of imported solar equipment | High |  | $27,400 (2.28%) | 5 wks | Procurement Manager |  | Order early; dual-source; penalty clause and expediting allowance. |  | $8,000 | TRANSFER |  |
| 3 | Material breakage during handling, storage, or contractor handover | Medium |  | $22,000 (1.83%) | 2 wks | Construction Manager |  | Inspection at receipt; protected storage; handling method statement; supplier/contractor liability. |  | $5,000 | TRANSFER |  |
| 4 | Contractor underperformance or default | Medium |  | $70,400 (5.87%) | 8 wks | Project Manager |  | Prequalify; performance bond; retention; milestone payments. Bond/admin premium affects direct cost. |  | $12,000 | MITIGATE |  |
| 5 | Scope creep from unapproved requests | High |  | $25,400 (2.12%) | 3 wks | Project Manager |  | Formal change control and baseline approval; allowance covers administration and impact analysis. |  | $3,000 | MITIGATE |  |
| 6 | Utility connection / net-metering delay | Medium |  | $8,800 (0.73%) | 4 wks | Sustainability Engineer |  | Apply early; temporary generator/testing arrangement. |  | $7,500 | MITIGATE |  |
| 7 | Local cement and steel price inflation | High |  | $35,200 (2.93%) | 0 wks | Procurement Manager |  | Although reporting is in USD, local purchases remain exposed to EGP supplier inflation and USD-equivalent escalation. Bulk-buy, fixed-price contracts, and secure storage. |  | $10,000 | MITIGATE |  |
| 8 | Site safety incident | Medium |  | $19,600 (1.63%) | 2 wks | QHSE Officer |  | Insurance; permit-to-work; edge protection; PPE and weekly toolbox talks. |  | $15,000 | MITIGATE |  |
| Total Potential Cost Impact |  |  | Total Potential Delay |  |  |  | Total Mitigation Cost |  | Reserve Check |  |  |
| $226,400 (18.87%) |  |  | 28 weeks (worst case, unmitigated) |  |  |  | $66,500 (5.54%) |  | $66,500 ≤ $78,000 contingency reserve |  |  |